## Build Out Plan
Type | Phase | No. | Description |  | Asset standing in Particular Phase? | [11 empty] | Comments
|  |  |  | Phase | Now | After Utility Diversions / current demolition work | Phase 1A | Phase 1B | Phase 2 | Phase 3 | Phase 4 | Phase 5 | Phase 6 | Phase 7 | Phase 8 | Ultimate
|  |  |  | Start Year | 2019 | 2019 | 2020 | 2021 | 2022 | 2027 | 2028 | 2028 | 2035 | 2040 | 2050 | 2050
|  |  |  | Complete Year | 2019 | 2019 | 2022 | 2023 | 2028 | 2029 | 2032 | 2037 | 2037 | 2040 | 2050 | 2050
Existing | 1 | 01 | MOH Quarantine |  | Yes | No | - | - | - | - | - | - | - | - | - | - |  | Yes
Existing | 1 | 02 | Clinic |  | Yes | No | - | - | - | - | - | - | - | - | - | - |  | No
Existing | 1 | 03 | Chandlers office |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 04 | "Canteen, Port works" |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 05 | Marine Workshop prayer room |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 06 | Marine Workshop prayer room TOILET BLOCK |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 07 | ROP Offices |  | Yes | Yes | Yes | No | - | - | - | - | - | - | - | -
Existing | 1 | 08 | MOTC Office |  | Yes | Yes | Yes | No | - | - | - | - | - | - | - | -
Existing | 1 | 09 | Laboratory |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 10 | ROP Customs Platform |  | Yes | Yes | Yes | No | - | - | - | - | - | - | - | -
Existing | 1 | 11 | Customs and Immigration |  | Yes | Yes | Yes | No | - | - | - | - | - | - | - | -
Existing | 1 | 11 | X-Ray |  | Yes | Yes | No | - | - | - | - | - | - | - | - | - | not required for operation, ROP to be notified to clear from site
Existing | 1 | 12 | "Canopy, VIP" |  | Yes | Yes | No | - | - | - | - | - | - | - | - | - | Need to relocate to outer gate/ waiting shed
Existing | 1 | 13 | Coffee Shop |  | Yes | Yes | No | - | - | - | - | - | - | - | - | - | not operational, opertor not cleared from site
Existing | 1 | 14 | "Cabin, Temporary" |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 15 | Document Archive |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 16 | Customs Control Point |  | Yes | Yes | No | - | - | - | - | - | - | - | - | - | Need to relocate to suitabile place, not part of currrent demolition work
Existing | 1 | 16 | GSM Telecom Tower |  | Yes | Yes | Yes | Yes | - | - | - | - | - | - | - | - | Ooreddo telecom tower, on mountain edge, agreement upto 2023
Existing | 1 | 16 | Gate Pass Center |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 17 | Claims Office |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 18 | Accomodation Marine Staff |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 19 | Septic Tanks |  | Yes | Yes | Yes | No | - | - | - | - | - | - | - | - | connected to item 1-11
Existing | 1 | 20 | WaterTank |  | Yes | Yes | Yes | - | - | - | - | - | - | - | - | - | need to check status
Existing | 1 | 21 | Parking / coffee shop |  | no |  |  | - | - | - | - | - | - | - | - | -
Existing | 1 | 22 | "Cabins, Various" |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 23 | Royal Yacht Compound |  | Yes | No | - | - | - | - | - | - | - | - | - | - | expect to handover bldg by end April19, and demolition later
Existing | 1 | 24 | Shed No.10 |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 25 | "Navy Storage, Various" |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 26 | Cement Silo |  | Yes | No | - | - | - | - | - | - | - | - | - | - | existing at site, hope to clear by mid May 2019
Existing | 1 | 26a | Cement Bagging Plant & Marine workshop |  | Yes | No | - | - | - | - | - | - | - | - | - | - | existing at site, hope to clear by mid May 2019
Existing | 1 | 27 | "Oman Fish Co.," |  | No |  | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 28 | Sheh Fuel Tank compound |  | Yes | No | - | - | - | - | - | - | - | - | - | - | likely to be opertional till Aug 19, and decommission later
Existing | 1 | 29 | Reefer Plugs |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 29 | Old Fish Market |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 30 | Parking |  | No | - | - | - | - | - | - | - | - | - | - | - | temperory car parking / with marked slot
Existing | 1 | 31 | MM office |  | Yes | No | - | - | - | - | - | - | - | - | - | - | need to double check
Existing | 1 | 33 | Port Entrance |  | Yes | Yes | Yes | No | - | - | - | - | - | - | - | - | connect with new traffic diversion plan / relocation of check post
Existing | 1 | 34 | ROP Coastguard |  | Yes | Yes | - | - | - | - | - | - | - | - | - | - | relocation date not finalised , waiting for ROP coast guard final plan
Existing | 1 | 35 | Ice Factory (old) |  | Yes | Yes | NO | - | - | - | - | - | - | - | - | - | new area identified, relocation date not final
Existing | 1 | 35a | Fishing shed |  | No |  | - | - | - | - | - | - | - | - | - | - | not existing now
Existing | 1 | 37 | Fridge Shed |  | no |  | - | - | - | - | - | - | - | - | - | - | not existing now
Existing | 1 | 37a | Fridge Shed |  | no |  | - | - | - | - | - | - | - | - | - | - | not existing now
Existing | 1 | 38 | Royal Yacht Compound |  | Yes | Yes | No | - | - | - | - | - | - | - | - | - | expect to handover bldg by end April19, and demolition later
Existing | 1 | 39 | ROP Coastguard |  | Yes | Yes | - | - | - | - | - | - | - | - | - | - | relocation date not finalised , waiting for ROP coast guard final plan
Existing | 1 | 50a | Bitumen Terminal Office |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 90 | "Fencing,Various" |  | Yes | Yes | Yes | - | - | - | - | - | - | - | - | - | demolition not scheduled
Existing | 1 | 91 | "Fencing,Various" |  | Yes | Yes | Yes | - | - | - | - | - | - | - | - | - | demolition not scheduled
Existing | 1 | 91 | Gate-guard roundabout |  | Yes | Yes | Yes | - | - | - | - | - | - | - | - | - | no gate guard at this point
Existing | 1 | 92 | Unsurveyed hard-standings |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Existing | 1 | 92a | Unsurveyed hard-standings |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Existing | 1 | CG01 | Taxi Driver Rest |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | -
Existing | 1 | CG02 | Parking |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | -
Existing | 1 | CG03 | CG Offices |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | Could be used for other purpose, upon shifting CG - HQ by ROP
Existing | 1 | CG05 | Parking |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | -
Existing | 1 | CG06 | Coastguard HQ office |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | Could be used for relocation of item 11, half building falls in phase 1
Existing | 1 | CG07 | Police station and port security |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | need to identify new location by 20207
Existing | 1 | CG08 | Septic Tank Housing |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | partially in Phase 1 area?
Existing | 1 | CG09 | "Fencing,Various" |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | alternative arrangement require ?? Base of mountain
Existing | 1 | RP10 | Customs and Immigration platform |  | Yes | Yes | No | - | - | - | - | - | - | - | - | - | not included in current demolition plan ? Alternative location for inspection ??
Existing | 2 | 30 | STS Cranes |  | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | - | not in operation, waiting for auction clearance by GOVT
Existing | 2 | 30 | STS Crane |  | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | - | not in operation, waiting for auction clearance by GOVT
Existing | 2 | 40 | Cruise Terminal Building & Control Tower |  | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | - | alternative port control room / ROP -custom facility / cruise terminal, to be ready
Existing | 2 | 50 | Bitumen Terminal |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | 2 | 54 | Shed 8 |  | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | -
Existing | 2 | 57 | Shed 7 |  | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | -
| 2 |  | Kiosk (@ corner - shed 8/ berth side) |  | Yes | Yes | Yes | Yes | No | [7 empty] | not in use
| 2 |  | WC (@ corner - shed 8/ bitumen plant) |  | Yes | Yes | Yes | Yes | No | [7 empty] | public facility /readiness of alternative facility
| 2 |  | Septic Tank (@ corner - shed 8/ bitumen plant) |  | Yes | Yes | Yes | Yes | No | [7 empty] | public facility /readiness of alternative facility
Kiosk (@ corner - shed 7/ berth side
Existing | 2 | 58 | Chiller Plant |  | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | - | link to item 40
Existing | 2 | 59 | WC |  | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | - | public facility /readiness of alternative facility
Existing | 2 | 60 | Septic Tank |  | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | - | public facility /readiness of alternative facility
Existing | 2 | 61 | Yard Cranes ( 5 nos) |  | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | - | not in operation, waiting for auction clearance by GOVT
Existing | 2 | 64 | Crane Wheel turning pads ( 12 locations) |  | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | - | not in operation, link to item 61 ( 12 locations)
power sockets / feeder pillers ( of old reefer yard) - 40 nos
Existing | 2 | 67 | Rail Track |  | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | - | link to item 30
Existing | 3 | 33 | Kiosk |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | not in use
Existing | 3 | 62 | WC |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | public facility /readiness of alternative facility
Existing | 3 | 63 | Container Terminal Office |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | not in use by port operator, temperorily used by MTDC contractor
Existing | 3 | 65 | Shed 3 |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | now in use by port operator
Existing | 3 | 72 | Gatepass |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | -
Existing | 3 | 73 | Fuel and Engineering worker WC and Wash |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | in use by Port operator / alternative arrangement required
Existing | 3 | 74 | Washing & Lubrication |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | in use by Port operator / alternative small workshop facility required
Existing | 3 | 75 | Engineering Wkshop |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | in use by Port operator / alternative small workshop facility required
Existing | 3 | 76 | Fuel and Engineering worker prayer room |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | in use by Port operator / alternative facility required
Existing | 3 | 77 | Restroom |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | in use by Port operator / alternative facility required
Existing | 3 | 78 | U/grnd Fuel Dispenser |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | not in use
|  |  | U/grond Fuel storage tank |  | Yes | Yes | Yes | Yes | Yes | No | [6 empty] | not in use
|  |  | U/grond Fuel storage tank |  | Yes | Yes | Yes | Yes | Yes | No | [6 empty] | not in use
Existing | 3 | 79 | EngineeringBuilding |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | in use by Port operator / alternative facility required
Existing | 3 | 80a | Parking |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | in use by Port operator / alternative facility required
Existing | 3 | 82 | Washing & Lubrication |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | not in use
Existing | 4 | 66 | wc |  | Yes | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | not in use
Existing | 4 | 66b | Transfer Yard Office - Transformer yard / Sub station (SS4) |  | Yes | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | Power supply to STS cranes not in use, Omanflour mill cranes in use , strret light and workshop facility) - needs alternative solution
Existing | 4 | 67 | Rail Track Buffers |  | Yes | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | linked to item 68
Existing | 4 | 68 | STS Cranes ( 3 nos) |  | Yes | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | not in operation, waiting for auction clearance by GOVT
|  |  | kiosk / coffee shop | [13 empty] | in use
Existing | 4 | 69 | Ramp |  | Yes | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | -
Existing | 4 | 70 | Grain Supply Switchgear |  | Yes | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | in use by Oman flour mill - needs alternative
Existing | 4 | 71 | SteelPlatform |  | Yes | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | -
Existing | 4 | 95 | Grain Unloader - 2 nos |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | bulk cargo unloader - equipment owned by OFMC
Existing | 5 | 83 | Oasis Fuel |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | future plan / logic of fuel supply to RY / other vessels
Existing | 5 | 85 | Substation ( Primary) |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | readiness of alternative facility
Existing | 5 | 87 | Switchgear / power sockets / feeder pillers ( of old reefer yard) - 30 nos |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | not in use
Existing | 5 | 87a | Switchgear / power sockets / feeder pillers ( of old reefer yard) - 30 nos |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | not in use
Yard Cranes ( 5 nos)
Crane Wheel turning pads ( 10 locations)
Existing | 5 | 96 | CFS shed |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | - | - | - | -
Existing | 8 | 100 | "Fencing,Various" |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | - | fencing across boundary - alternative ??
Existing | 8 | 100a | "Fencing,Various" |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | - | fencing across boundary - alternative ??
Existing | HS | A | Ancient Fort |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Existing | HS | B | Ancient Fort |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Existing | HS | C | Ancient Graveyard |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Existing | HS | E | Ancient Graveyard |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Existing | RY | 01 | Fuel Dispenser |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | not affecting , RY likely to shift to have new building
Existing | RY | 02 | Water Tank |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | not affecting , RY likely to shift to have new building
Existing | RY | 03 | Shell Fuel |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | not affecting , RY likely to shift to have new building
Existing | RY | 04 | Shed / store room |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Existing | RY | 05 | Storage / VIP guest room |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Existing | RY | 06 | Store / Guard room |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Existing | ST | 01 | Substation |  | Yes | No | - | - | - | - | - | - | - | - | - | - | Relocated and renamed ESS8
Existing | ST | 02 | Substation |  | Yes | Yes | Yes | No | - | - | - | - | - | - | - | - | feeding STS cranes at berth 4&5, not in use, shed 7 , shed 8 , HMLs
Existing | ST | 03 | Substation |  | Yes | No | - | - | - | - | - | - | - | - | - | - | Relocated and renamed ESS3
|  | 04 | Substation |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  | till suitable replacement / part for OFMC Cranes
Existing | ST | 05 | Substation |  | Yes | No | - | - | - | - | - | - | - | - | - | - | Relocated and renamed ESS5
Existing | ST | 06 | Substation |  | Yes | Yes | Yes | Yes | Yes | no | - | - | - | - | - | - | Required until removal of Gatehouse , CG06 , CG 07
|  | 07 | Substation |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No |  |  |  |  | till suitable replacement / CFS / Fuel tank/HML
Existing | ST | 08 | Substation |  | Yes | No | - | - | - | - | - | - | - | - | - | - | Relocated and renamed ESS8
Existing | ST | 09 | Substation |  | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | - | to feed cruise terminal building
Existing | X | 01 | Unsurveyed tank |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Existing | X | 02 | Unsurveyed tank compouind |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | water tank (old) not in use
Existing | X | 2 | Unsurveyed tank compouind |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Existing | X | 80 | Silos, National Grain - 01-303 on Development Plan |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Existing | X | 80a | "National Grain, buildings" |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Possibly conveyor belt? Staff rest room / toilet / prayer rooms
underground services potable water
services potable water within tunnel
underground services fuel lines
services fuel lines within tunnel
underground services storm water
underground services OFMC - conveyour
underground - electrical HT / LV CABLES
underground - TELEPHONE cables
underground - IT / fibre optic network
high mast lights
street lights
Firehydrants ( undeground)
Fire horse reel cabinets
New | 1 | 101 | Mixed Use |  | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | 102 | Residential |  | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | 201 | Retail/Commercial |  | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | 202 | Parking |  | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | 203 | Parking |  | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | 204 | Hotel |  | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | 205 | Cultural |  | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | 301 | Utilities |  | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | 302 | Utilities |  | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | 305 | Utilities |  | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | 401 | Open Space |  | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | 501 | Utilities |  | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | 601 | Utilities |  | No | No | No | No | No | No | No | No | No | No | No | No | Based on current assumption, no need for STP
New | 1 | L01 | Open Space |  | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | R01 | Roads |  | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | R02 | Roads |  | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | R03 | Roads |  | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | R04 | Roads |  | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | R05 | Roads |  | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | L02 | Open Space |  | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 2 | 1 | Residential |  | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 2 | L01 | Open Space |  | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 3 | 101 | Retail/Commercial |  | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 3 | 102 | Hotel |  | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 3 | 105 | Utilities |  | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 3 | 401 | Cultural |  | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 3 | 505 | Historic Fort |  | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 3 | L02 | Open Space |  | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 3 | L04 | Open Space |  | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 3 | L05 | Open Space |  | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 3 | L06 | Open Space |  | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 3 | L11 | Open Space |  | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 3 | R01 | Roads |  | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 3 | L03 | Open Space |  | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 4 | 100 | Residential |  | No | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes
New | 4 | 200 | Residential |  | No | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes
New | 4 | 301 | Hotel |  | No | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes
New | 4 | 401 | Utilities |  | No | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes
New | 4 | L01 | Open Space |  | No | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes
New | 4 | R01 | Roads |  | No | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes
New | 5 | 100 | Residential |  | No | No | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes
New | 5 | L01 | Open Space |  | No | No | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes
New | 5 | L02 | Open Space |  | No | No | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes
New | 5 | L03 | Open Space |  | No | No | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes
New | 6 | 101 | Hotel |  | No | No | No | No | No | No | No | No | Yes | Yes | Yes | Yes
New | 7 | 101 | Parking |  | No | No | No | No | No | No | No | No | No | Yes | Yes | Yes
New | 7 | 102 | Parking |  | No | No | No | No | No | No | No | No | No | Yes | Yes | Yes
New | 7 | 103 | Parking |  | No | No | No | No | No | No | No | No | No | Yes | Yes | Yes
New | 7 | 104 | Parking |  | No | No | No | No | No | No | No | No | No | Yes | Yes | Yes
New | 1A | TW1 | Temporary Surface Parking at 01.205 |  | No | No | Yes | No | - | - | - | - | - | - | - | -
New | 1A | TW2 | Temporary Surface Parking at 01.204, 01.202, 01.203, 01.201 |  | No | No | Yes | No | - | - | - | - | - | - | - | -
New | U | ESS3 | Relocated Substation 3 |  | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Previous ST 03
New | U | ESS5 | Relocated Substation 5 |  | No | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | Previous ST 05A and 05b - not relocating
New | U | ESS8 | Relocated Substation 8 |  | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Previous ST 01 and 08
underground services potable water
underground services fuel lines
underground services storm water
underground services OFMC - conveyour
service tunnels across berths
underground - electrical HT / LV CABLES
underground - TELEPHONE cables
underground - IT / fibre optic network
high mast lights
street lights

## Connection Plan
Type | Phase | No. | Description |  | Asset connection needed in each phase? | [11 empty] | Comments
|  |  |  | Phase | Now | After Utility Diversions | Phase 1A | Phase 1B | Phase 2 | Phase 3 | Phase 4 | Phase 5 | Phase 6 | Phase 7 | Phase 8 | Ultimate
|  |  |  | Start Year | 2019 | 2019 | 2020 | 2021 | 2022 | 2027 | 2028 | 2028 | 2035 | 2040 | 2050 | 2050
|  |  |  | Complete Year | 2019 | 2019 | 2022 | 2023 | 2028 | 2029 | 2032 | 2037 | 2037 | 2040 | 2050 | 2050
Existing | 1 | 01 | MOH Quarantine |  | Yes | No | - | - | - | - | - | - | - | - | - | - |  | Yes
Existing | 1 | 02 | Clinic |  | Yes | No | - | - | - | - | - | - | - | - | - | - |  | No
Existing | 1 | 03 | Chandlers office |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 04 | "Canteen, Port works" |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 05 | Marine Workshop |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 06 | Marine Workshop prayer room |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 07 | ROP Offices |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 08 | MOTC Office |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 09 | Laboratory |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 10 | ROP Customs Platform |  | Yes | Yes | Yes | No | - | - | - | - | - | - | - | -
Existing | 1 | 11 | Customs and Immigration |  | Yes | Yes | Yes | No | - | - | - | - | - | - | - | -
Existing | 1 | 11 | X-Ray |  | Yes | No | - | - |  | - | - | - | - | - | - | -
Existing | 1 | 12 | "Canopy, VIP" |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 13 | Coffee Shop |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 14 | "Cabin, Temporary" |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 15 | Document Archive |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 16 | Customs Control Point |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 16 | GSM Telecom Tower |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 16 | Gate Pass Center |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 17 | Claims Office |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 18 | Accomodation Marine Staff |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 19 | Septic Tanks |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 20 | WaterTank |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 21 | Parking |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 22 | "Cabins, Various" |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 23 | Royal Yacht Compound |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 24 | Shed No.10 |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 25 | "Navy Storage, Various" |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 26 | Cement Silo |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 26a | Cement Bagging Plant |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 27 | "Oman Fish Co.," |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 28 | Sheh Fuel Tank compound |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 29 | Reefer Plugs |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 29 | Old Fish Market |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 30 | Parking |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 31 | MM office |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 33 | Port Entrance |  | Yes | Yes | Yes | No | - | - | - | - | - | - | - | -
Existing | 1 | 34 | ROP Coastguard |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 35 | Ice Factory (old) |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 35a | Fishing shed |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 37 | Fridge Shed |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 37a | Fridge Shed |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 38 | Royal Yacht Compound |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 39 | ROP Coastguard |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 50a | Bitumen Terminal Office |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 90 | "Fencing,Various" |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 91 | "Fencing,Various" |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 91 | Gate-guard roundabout |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 92 | Unsurveyed hard-standings |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | 1 | 92a | Unsurveyed hard-standings |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | 1 | CG01 | Taxi Driver Rest |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | 1 | CG02 | Parking |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | 1 | CG03 | CG Offices |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | -
Existing | 1 | CG05 | Parking |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | 1 | CG06 | Coastguard HQ office |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | -
Existing | 1 | CG07 | Police station and port security |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | -
Existing | 1 | CG08 | Septic Tank Housing |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | 1 | CG09 | "Fencing,Various" |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | 1 | RP10 | Customs and Immigration platform |  | Yes | No | - | - | - | - | - | - | - | - | - | -
Existing | 2 | 30 | STS Cranes |  | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | -
Existing | 2 | 30 | STS Crane |  | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | -
Existing | 2 | 40 | Terminal Building & Control Tower |  | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | -
Existing | 2 | 50 | Bitumen Terminal |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | 2 | 54 | Shed 8 |  | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | -
Existing | 2 | 57 | Shed 7 |  | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | -
Existing | 2 | 58 | Chiller Plant |  | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | -
Existing | 2 | 59 | WC |  | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | -
Existing | 2 | 60 | Septic Tank |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | 2 | 61 | Yard Cranes |  | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | -
Existing | 2 | 64 | Crane Wheel |  | Yes | Yes | Yes | Yes | No | - | - | - | - | - | - | -
Existing | 2 | 67 | Rail Track |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | 3 | 33 | Kiosk |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | -
Existing | 3 | 62 | WC |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | -
Existing | 3 | 63 | Container Terminal Office |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | -
Existing | 3 | 65 | Shed 3 |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | -
Existing | 3 | 72 | Gatepass |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | -
Existing | 3 | 73 | Fuel and Engineering worker WC and Wash |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | -
Existing | 3 | 74 | Washing & Lubrication |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | -
Existing | 3 | 75 | Engineering Wkshop |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | -
Existing | 3 | 76 | Fuel and Engineering worker prayer room |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | -
Existing | 3 | 77 | Restroom |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | -
Existing | 3 | 78 | U/grnd Fuel Dispenser |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | -
Existing | 3 | 79 | EngineeringBuilding |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | -
Existing | 3 | 80a | Parking |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | 3 | 82 | Washing & Lubrication |  | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | - | -
Existing | 4 | 66 | wc |  | Yes | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | -
Existing | 4 | 66b | Transfer Yard Office |  | Yes | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | -
Existing | 4 | 67 | Rail Track Buffers |  | Yes | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | -
Existing | 4 | 68 | STS Cranes |  | Yes | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | -
Existing | 4 | 69 | Ramp |  | Yes | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | -
Existing | 4 | 70 | Grain Supply Switchgear |  | Yes | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | -
Existing | 4 | 71 | SteelPlatform |  | Yes | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | -
Existing | 4 | 95 | Grain Unloader |  | Yes | Yes | Yes | Yes | Yes | Yes | No | - | - | - | - | -
Existing | 5 | 83 | Oasis Fuel |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | - | - | - | -
Existing | 5 | 85 | Substation |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | - | - | - | -
Existing | 5 | 87 | Switchgear |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | - | - | - | -
Existing | 5 | 87a | Switchgear |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | - | - | - | -
Existing | 5 | 96 | CFS shed |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | - | - | - | -
Existing | 8 | 100 | "Fencing,Various" |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | 8 | 100a | "Fencing,Various" |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | HS | A | Ancient Fort |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | HS | B | Ancient Fort |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | HS | C | Ancient Graveyard |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | HS | E | Ancient Graveyard |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | RY | 01 | Fuel Dispenser |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Existing | RY | 02 | Water Tank |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Existing | RY | 03 | Shell Fuel |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Existing | RY | 04 | Shed |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Existing | RY | 05 | Storage |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Existing | RY | 06 | Store |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Existing | ST | 01 | Substation |  | Yes | No | - | - | - | - | - | - | - | - | - | - | Relocated and renamed ESS8
Existing | ST | 02 | Substation |  | Yes | Yes | Yes | No | - | - | - | - | - | - | - | -
Existing | ST | 03 | Substation |  | Yes | No | - | - | - | - | - | - | - | - | - | - | Relocated and renamed ESS3
Existing | ST | 05 | Substation |  | Yes | No | - | - | - | - | - | - | - | - | - | - | Relocated and renamed ESS5
Existing | ST | 06 | Substation |  | Yes | Yes | Yes | No | - | - | - | - | - | - | - | - | Required until removal of Gatehouse
Existing | ST | 08 | Substation |  | Yes | No | - | - | - | - | - | - | - | - | - | - | Relocated and renamed ESS8
Existing | ST | 09 | Substation |  | Yes | Yes | Yes | No | - | - | - | - | - | - | - | -
Existing | X | 01 | Unsurveyed tank |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | X | 02 | Unsurveyed tank compouind |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | X | 2 | Unsurveyed tank compouind |  | No | - | - | - | - | - | - | - | - | - | - | -
Existing | X | 80 | Silos, National Grain - 01-303 on Development Plan |  | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Existing | X | 80a | "National Grain, buildings" |  | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Possibly conveyor belt?
New | 1 | 101 | Mixed Use |  | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | 102 | Residential |  | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | 201 | Retail/Commercial |  | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | 202 | Parking |  | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | 203 | Parking |  | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | 204 | Hotel |  | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | 205 | Cultural |  | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | 301 | Utilities |  | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | 302 | Utilities |  | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | 305 | Utilities |  | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | 401 | Open Space |  | No | No | No | No | No | No | No | No | No | No | No | No
New | 1 | 501 | Utilities |  | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | 601 | Utilities |  | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Based on current assumption, no need for STP
New | 1 | L01 | Open Space |  | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | R01 | Roads |  | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | R02 | Roads |  | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | R03 | Roads |  | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | R04 | Roads |  | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | R05 | Roads |  | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 1 | L02 | Open Space |  | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 2 | 1 | Residential |  | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 2 | L01 | Open Space |  | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 3 | 101 | Retail/Commercial |  | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 3 | 102 | Hotel |  | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 3 | 105 | Utilities |  | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 3 | 401 | Cultural |  | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 3 | 505 | Historic Fort |  | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 3 | L02 | Open Space |  | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 3 | L04 | Open Space |  | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 3 | L05 | Open Space |  | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 3 | L06 | Open Space |  | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 3 | L11 | Open Space |  | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes
New | 3 | R01 | Roads |  | No | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes
New | 3 | L03 | Open Space |  | No | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes
New | 4 | 100 | Residential |  | No | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes
New | 4 | 200 | Residential |  | No | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes
New | 4 | 301 | Hotel |  | No | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes
New | 4 | 401 | Utilities |  | No | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes
New | 4 | L01 | Open Space |  | No | No | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes
New | 4 | R01 | Roads |  | No | No | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes
New | 5 | 100 | Residential |  | No | No | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes
New | 5 | L01 | Open Space |  | No | No | No | No | No | No | No | Yes | Yes | Yes | Yes | Yes
New | 5 | L02 | Open Space |  | No | No | No | No | No | No | No | No | Yes | Yes | Yes | Yes
New | 5 | L03 | Open Space |  | No | No | No | No | No | No | No | No | No | Yes | Yes | Yes
New | 6 | 101 | Hotel |  | No | No | No | No | No | No | No | No | No | Yes | Yes | Yes
New | 7 | 101 | Parking |  | No | No | No | No | No | No | No | No | No | Yes | Yes | Yes
New | 7 | 102 | Parking |  | No | No | No | No | No | No | No | No | No | Yes | Yes | Yes
New | 7 | 103 | Parking |  | No | No | Yes | No | Yes | No | No | No | No | No | No | No
New | 7 | 104 | Parking |  | No | No | Yes | No | Yes | No | No | No | No | No | No | No
New | 1A | TW1 | Temporary Surface Parking at 01.205 |  | No | No | Yes | No
New | 1A | TW2 | Temporary Surface Parking at 01.204, 01.202, 01.203, 01.201 |  | No | No | Yes | No
New | U | ESS3 | Relocated Substation 3 |  | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Previous ST 03
New | U | ESS5 | Relocated Substation 5 |  | No | Yes | Yes | Yes | No | - | - | - | - | - | - | - | Previous ST 05A and 05b
New | U | ESS8 | Relocated Substation 8 |  | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Previous ST 01 and 08